## Cover Sheet
CONFIDENTIAL INFORMATION This document and the information contemplated therein have to be considered as Confidential Information pursuant to the provisions of Clause 25 of the MSA, and treated as such
RELEASED | [7 empty] | Application: PRASA
Technical Modifications |  |  |  | Geometric tolerances |  |  | A4 |  |  |  | N
[6 empty] | Replaces : |  |  | Replaced by :
A0 | Creation
Index | Revision Notification no.
|  | Prepared | Mbuso | Mabena | Change Request Tracker Baseline 10.4_TS223
|  | Checked | Ntsako | Salani
|  | Approved | Lethabo | Shilakoe
|  |  | Date | Name
|  |  | en | 2024-05-22
|  |  | GIB0000006849 | [6 empty] | A0

## Modification
TABLE OF MODIFICATIONS
Revision | Authors | Date | Tab | Object of the modification
A0 | Mbuso Mabena | 2024-05-22 | 5 | Change Request Tracker Baseline 10.4_TS223
| GIB0000006849 | A0 | Change Request Tracker Baseline 10.4_TS223 |  | 2024-05-22
| <Reference> | Rev |  |  | 2/5 Pages

## Validation
INTERNAL VALIDATION
| Name |  | Function | Signature
Writer | Mbuso Mabena |  | Intern: PrCCC
Checker | Ntsako Salani |  | PrCCC
Approver | Lethabo Shilakoe |  | PrCCM
| GIB0000006849 | A0 | Change Request Tracker Baseline 10.4_TS223 |  | 2024-05-22
| <Reference> | Rev |  |  | 3/5 Pages
This document and the information contemplated therein have to be considered as Confidential Information pursuant to the provisions of Clause 25 of the MSA, and treated as such

## Introduction
INTRODUCTION
Change Request Tracker is a document that provides information of changes applied per baseline. The information includes, change Request number, Change Request description, and the impacted cars. The tracker records and communicate the status of change request on the train with internal and external customers.
DEFINITION
Changes on the CR tracker are defined by the baseline.
ACRONYM
PBR: Product Breakdown Review TC: Trailer Car M: Motor Car KPI: Key performance Indicator CR: Change Request NA: Not Applicable
| GIB0000006849 | A0 | Change Request Tracker Baseline 10.4_TS223 | 2024-05-22
| <Reference> | Rev |  | 4/5 Pages

## CR Tracker BL10.4
BL10.3.1 | CR Title | TC1 | M4 | M1 | M2 | M3 | TC2 | Application Status | Comment
CR0041434 | Map Label with plastic reinforcement for SMC panel | Applied | Applied | Applied | Applied | Applied | Applied | 100%
CR0036671 | DD plates Restoration from S/Steel back to Alu | Applied | NA | NA | NA | NA | Applied | 100%
CR0033843 | Panto_Filter screen change from 40-to-5 microns | NA | NA | Applied | Applied | NA | NA | 100%
CR0033837 | Design of External livery and Marking | Applied | Applied | Applied | Applied | Applied | Applied | 100%
CR0032645 | Cab Door Hinge Protection_New Design | Applied | NA | NA | NA | NA | Applied | 100%
CR0041529 | CBS-Carbodyshell side closing 2D update | Applied | Applied | Applied | Applied | Applied | Appled | 100%
CR0039969 | Cab Door - Window Seal Dimension Changes | Applied | NA | NA | NA | NA | Applied | 100%
CR0039961 | Cab Door Handle Dimension Change | Applied | NA | NA | NA | NA | Applied | 100%
CR0039229 | INTERIOR_BENCH INSTALLATIONS_DRAUGHT SCREEN | Applied | Applied | Applied | Applied | Applied | Applied | 100%
CR0039165 | TRACTION CONVERTOR FILTER DOOR LOCKING MECHANISM F | Applied | Applied | Applied | Applied | Applied | Applied | 100%
CR0039152 | Bogie BoM and D2 Update - July 2020 | Applied | Applied | Applied | Applied | Applied | Applied | 100%
CR0038918 | Drainage pipe size unavailable locally seac scope | Applied | Applied | Applied | Applied | Applied | Applied | 100%
CR0038868 | Seamless tubes not available locally seac scope | Applied | Applied | Applied | Applied | Applied | Applied | 100%
CR0037427 | 2D DRAWINGS UPDATE - SHEET METAL PARTS | NA | Applied | Applied | Applied | Applied | NA | 100%
CR0037184 | Headstock Ubunye Change Proposals | Applied | Applied | Applied | Applied | Applied | Applied | 100%
CR0037034 | Door window film modified to suit window tolerance | Applied | Applied | Applied | Applied | Applied | Applied | 100%
CR0033875 | In order to comply with the requirements of local | Applied | Applied | Applied | Applied | Applied | Applied | 100%
CR0033862 | Profibre Products would like to propose a trim | Applied | Applied | Applied | Applied | Applied | Applied | 100%
CR0031881 | New cost reduced local door stop | Applied | NA | NA | NA | NA | Applied | 100%
CR0031740 | EUF C-RAILS | Applied | Applied | Applied | Applied | Applied | Applied | 100%
CR0032215 | Re-Design of Re-raling pin protection cover | Applied | Applied | Applied | Applied | Applied | Applied | 100%
CR0051181 | Bridge pieces of TB not aligning with SPC | Applied | NA | NA | NA | NA | Applied | 100%
CR0041468 | Supporting base interface plate angle change | Applied | NA | NA | NA | NA | Applied | 100%
CR0040737 | HVAC controller localisation | Applied | Applied | Applied | Applied | Applied | Applied | 100%
CR0039618 | PFD00015- LV Cubicle Covers Warped | Applied | Applied | Applied | Applied | Applied | Applied | 100%
CR0039165 | TRACTION CONVERTOR FILTER DOOR LOCKING MECHANISM F | NA | Applied | Applied | Applied | Applied | NA | 100%
CR0038733 | Doorframe Localisation | Applied | Applied | Applied | Applied | Applied | Applied | 100%
CR0038608 | Cab External Lighting_Head_Platform and Tail light | Applied | NA | NA | NA | NA | Applied | 100%
CR0037891 | Hubner gangway side covering aesthetics solution | Applied | Applied | Applied | Applied | Applied | Applied | 100%
CR0037541 | UPDATING THE MISSING BEND RADIUS DIMENSION | Applied | Applied | Applied | Applied | Applied | Applied | 100%
CR0037314 | Removal of unused C rails; Bosses; Brackets and Ea | Applied | Applied | Applied | Applied | Applied | Applied | 100%
CR0035774 | Cab exterior_windscreen_ drawing update | Applied | NA | NA | NA | NA | Applied | 100%
CR0035425 | UPDATE_MISSING WELDING INFORMATION AND DIMENSIONS | NA | Applied | Applied | Applied | Applied | NA | 100%
CR0034151 | Manufacturing Process From RTM to SMC for Interior | Applied | Applied | Applied | Applied | Applied | Applied | 100%
CR0033382 | Validation of a new FILLER: HENKEL - Teroson PU 6 | Applied | Applied | Applied | Applied | Applied | Applied | 100%
CR0032104 | LATERAL FITTING TOP | Applied | Applied | Applied | Applied | Applied | Applied | 100%
CR0039683 | Change bosses in prep for wheel flange lubrication | Applied | Applied | Applied | Applied | Applied | Applied | 100%
CR0033359 | Nose panel Gaps Improvement: Anti Intrusion Box | Applied | NA | NA | NA | NA | Applied | 100%
CR0039652 | Bottom Skirt Installation- Incorrect Shims | Applied | Applied | Applied | Applied | Applied | Applied | 100%
CR0049641 | Couplers: spring plates and centring element_material | Applied | Applied | Applied | Applied | Applied | Applied | 100%
CR0037898 | Damaged wires on MASU Isolation Cock | Applied | NA | NA | NA | NA | Applied | 100%
CR0037476 | Saloon window film marking - apply tape to gutters | Applied | Applied | Applied | Applied | Applied | Applied | 100%
CR0037164 | FOLDED SHEET 890X275X2 2D update_Tolerance correct | Applied | Applied | Applied | Applied | Applied | Applied | 100%
CR0037151 | Seac drawing updates | Applied | Applied | Applied | Applied | Applied | Applied | 100%
CR0035710 | Cab/Partition Door cam lock-key number correction | Applied | NA | NA | NA | NA | Applied | 100%
CR0035626 | Brakes_Mono-stable valve_Application of Mod 3 Mono | Applied | Applied | Applied | Applied | Applied | Applied | 100%
CR0035475 | Underframe M1M2_Aux air prod equipt_Covers | NA | NA | Applied | Applied | NA | NA | 100%
CR0033860 | Air Production_MASU_Air Humidity Indicator Design | Applied | NA | NA | NA | NA | Applied | 100%
CR0051812 | Roof Assy_Extension of seamless weld to avoid wavi | Applied | NA | NA | NA | NA | Applied | 100%
CR0037190 | Addition of New Collar Reference on Cab Air Duct | Applied | NA | NA | NA | NA | Applied | 100%
CR0032379 | pneumatic horns are not emitting required noise l | Applied | NA | NA | NA | NA | Applied | 100%
CR0049326 | HVAC_Support_Roof_HVAC brackets are aesthetically unacceptable | Applied | Applied | Applied | Applied | Applied | Applied | 100%
CR0039673 | Baseboard duct removal | Applied | Applied | Applied | Applied | Applied | Applied | 100%
CR0035718 | Master controller deadman is sticky | Applied |  |  |  |  | Applied | 100%
CR0036183 | Gangway add profile cut outs and shorten bolts | Applied | Applied | Applied | Applied | Applied | Applied | 100%
CR0039015 | Removal of paint on AI box earthing points | Applied | NA | NA | NA | NA | Applied
CR0039877 | Gangway removal of flap covering end profile bolts | Applied | Applied | Applied | Applied | Applied | Applied | 100%
CR0047039 | New passenger door EAD | Applied | Applied | Applied | Applied | Applied | Applied | 100%
CR0047642 | Floor covering (vinyl) welding change | Applied | Applied | Applied | Applied | Applied | Applied | 100%
CR0044285 | Cab Door key plate thread holes change to Hexerts | Applied | NA | NA | NA | NA | Applied | 100%
CR0037326 | cable trays welding reduction | Applied | Applied | Applied | Applied | Applied | Applied | 100%
Future Baselines Changes Applied in Advance |  | TC1 | M4 | M1 | M2 | M3 | TC2 | Application Status | Comment
CR0032288 | EUF Identification plate PRASA Request | Applied | Applied | Applied | Applied | Applied | Applied | 100% | BL10.5
CR0052117 | BoM structure change on DMA for FIRE EXTINGUISHER BRACKET | Applied | Applied | Applied | Applied | Applied | Applied | 100% | BL10.6
CR0049722 | TPS Strips Adhesive update ext. livery placement | Applied | Applied | Applied | Applied | Applied | Applied | 100% | BL10.6
CR0045079 | Change of AIB sealant from GREY to BLACK colour | Applied | NA | NA | NA | NA | Applied | 100% | BL10.6
CR0042715 | Driver seat part number split | Applied | NA | NA | NA | NA | Appled | 100% | BL10.6
CR0041021 | Front coupler cabling Incorrect E.BOM | Applied | NA | NA | NA | NA | Applied | 100% | BL10.6
CR0044711 | CVS Interior Lighting Revision 13 Installation | Applied | Applied | Applied | Applied | Applied | Applied | 100% | BL10.6
CR0040687 | LV CUBICLE LINING BOTTOM RADIUS INCREASE | Applied | Applied | Applied | Applied | Applied | Applied | 100% | BL10.6
CR0039370 | Bottom protection cover change of material | Applied | Applied | Applied | Applied | Applied | Applied | 100% | BL10.6
CR0047644 | EUF ID Label :The stainless steel material is hard for engraving, thus aluminium is OK for engraving | Applied | Applied | Applied | Applied | Applied | Applied | 100% | BL10.5
CR0036030 | No connector labelling on face of END frame | Applied | Applied | Applied | Applied | Applied | Applied | 100% | BL10.5
CR0047261 | WARNING SIGN NOT INCLUDED ON HV TERMINAL BLOCK TPS | Applied | Applied | Applied | Applied | Applied | Applied | 100% | BL10.5
CR0039164 | Car bodyside damage - apply film as containment | Applied | Applied | Applied | Applied | Applied | Applied | 100% | BL10.5
CR0045741 | Change from MAKE-BUY - Cable trays_2mm locating holes. | Applied | Applied | Applied | Applied | Applied | Applied | 100% | BL10.5
CR0055016 | Secondary suspension support change to forged | Applied | Applied | Applied | Applied | Applied | Applied | 100% | BL10.5
CR0053831 | Pneumatic Horns Design Changes | Applied | NA | NA | NA | NA | Applied | 100% | BL10.5
CR0051302 | Input filter EB removal | NA | Applied | Applied | Applied | Applied | NA | 100% | BL10.5
CR0049743 | New part number for HVAC | Applied | Applied | Applied | Applied | Applied | Applied | 100% | BL10.5
CR0049338 | BL10.3 LHD update | Applied | Applied | Applied | Applied | Applied | Applied | 100% | BL10.5
CR0047973 | Inter-car Absobers_Addition of Socopac | Applied | Applied | Applied | Applied | Applied | Applied | 100% | BL10.5
CR0047654 | HVAC Aluminium alloy shortage | Applied | Applied | Applied | Applied | Applied | Applied | 100% | BL10.5
CR0047511 | Glazing-windscreen-windscreen demister removal | Applied | NA | NA | NA | NA | Applied | 100% | BL10.5
CR0046708 | Gangway floor covering detaching at car ends | Applied | Applied | Applied | Applied | Applied | Applied | 100% | BL10.5
CR0044804 | Underframe_Anti Slip Plate_Change of thickness | Applied | Applied | Applied | Applied | Applied | Applied | 100% | BL10.5
CR0044600 | ACU revision change B to D | Applied | NA | NA | NA | NA | Applied | 100% | BL10.5
CR0043235 | Gangway velcro at car end detatching - serial soln | Applied | Applied | Applied | Applied | Applied | Applied | 100% | BL10.5
CR0043048 | Floor panels flatness requiremnent update (TPS) | Applied | Applied | Applied | Applied | Applied | Applied | 100% | BL10.5
CR0042718 | Change of Front sunblind material color and opacit | Applied | NA | NA | NA | NA | Applied | 100% | BL10.5
CR0042716 | Addition of RAMS and Maintenance requirement on th | Applied | NA | NA | NA | NA | Applied | 100% | BL10.5
CR0040127 | DRIVER SEAT TEARING | Applied | NA | NA | NA | NA | Applied | 100% | BL10.5
CR0039676 | SMC DRAWINGS &amp; PARTS UPDATE | Applied | Applied | Applied | Applied | Applied | Applied | 100% | BL10.5
CR0039409 | ACU and DCU communicate at lower priority | Applied | Applied | Applied | Applied | Applied | Applied | 100% | BL10.5
CR0038198 | Air Production_AuxComp_Implementation from TS058 | NA | Applied | Applied | Applied | Applied | NA | 100% | BL10.5
CR0033737 | Cleaning of the bogie brake discs | Applied | Applied | Applied | Applied | Applied | Applied | 100% | BL10.5
CR0057437 | Battery cells are leaking on the valve and terminal | Applied | NA | NA | NA | NA | Applied | 100% | BL10.5
CR0057441 | Battery loss of capacity issue | Applied | NA | NA | NA | NA | Applied | 100% | BL10.5
CR0047640 | Change of Raw Material from Carbon to Stainless Steel on the Air Tanks | Applied | Applied | Applied | Applied | Applied | Applied | 100% | BL10.5
CR0037226 | Underframe Cabling_CL5B Cable_Conduit and hood | NA | Applied | Applied | Applied | Applied | NA | 100% | BL10.5
CR0032275 | Passenger Emergency Alarm Handle Stiff | Applied | Applied | Applied | Applied | Applied | Applied | 100% | BL10.5
CR0032270 | Passenger Emergency Alarm Auto Resets | Applied | Applied | Applied | Applied | Applied | Applied | 100% | BL10.5
CR0020982 | Replace Traction Box | Applied | Applied | Applied | Applied | Applied | Applied | 100% | BL10.5
CR0050817 | CVS agate failure | Applied | NA | NA | NA | NA | Applied | 100% | BL10.5
CR0047653 | HVAC water eliminator localisation | Applied | Applied | Applied | Applied | Applied | Applied | 100% | BL10.5
CR0033853 | MASU Oil Leaks - oil leaks were observed on several trains | Applied | NA | NA | NA | NA | Applied | 100% | BL10.5
CR0033330 | PLACEMENT OF ABB CONTACTORS in LV1 Cubicles | Applied | NA | NA | NA | NA | Applied | 100% | BL10.5
CR0048444 | HVAC Support_Roof_CBS | Applied | Applied | Applied | Applied | Applied | Applied | 100% | BL10.4.1
CR0060843 | Door leaf castle nut collides with Sealing Angle | Applied | Applied | Applied | Applied | Applied | Applied | 100% | BL10.6
CR0042890 | Water leaks through the CBS (Passenger doors) | Applied | Applied | Applied | Applied | Applied | Applied | 100% | BL10.6
CR0044711 | CVS Interior Lighting Revision 13 Installation | Applied | Applied | Applied | Applied | Applied | Applied | 100% | BL10.6
CR0032388 | MCE ? Work Instruction Update- Ethernet Cable | Applied | Applied | Applied | Applied | Applied | Applied | 100% | BL10.6
CR0057685 | UHF Radio Obsolete | Applied | NA | NA | NA | NA | Applied | 100% | BL10.5
CR0042280 | Passenger Door Sealing Angle ID label relocation | Applied | Applied | Applied | Applied | Applied | Applied | 100% | BL10.6
CR0033470 | Headlight Testing at Fitting All 4 stations | Applied | NA | NA | NA | NA | Applied | 100% | BL10.6
CR0049965 | Reversal of CR0029245 Cabin threshold protection | Applied | NA | NA | NA | NA | Applied | 100% | BL10.6
CR0054198 | Gibela logo improvement | Applied | NA | NA | NA | NA | Applied | 100% | BL10.6
CR0052099 | TC1-LV2 FDCU sidesprt Design for Manufacturability | Applied | NA | NA | NA | NA | NA | 100% | BL10.6
CR0044805 | Underframe_Lifting Pad_Change of thickness | Applied | Applied | Applied | Applied | Applied | Applied | 100% | BL10.6
CR0054255 | Air production_MASU_MASU oil separator explosion | Applied | NA | NA | NA | NA | Applied | 100% | BL10.6
CR0061460 | Tolerance and material change of re-railing pin cover | Applied | Applied | Applied | Applied | Applied | Applied | 100% | BL10.5
CR0041608 | Underframe cabling class 1 TC conduit too long | Applied | NA | NA | NA | NA | Applied | 100% | BL10.6
CR0051695 | Change Material size for Inter-car cables - M3 | NA | NA | NA | NA | Applied | Applied | 100% | BL10.6
CR0052629 | Update for Front Coupler Cabling-CL2_E.bom | Applied | NA | NA | NA | NA | Applied | 100% | BL10.6
CR0046669 | DD plates defected when torque tightening | Applied | NA | NA | NA | NA | Applied | 100% | BL10.6
CR0033798 | Input filter frame has been changed from bolted to |  | Applied | Applied | Applied | Applied | Applied | 100% | BL10.6
CR0042875 | Gangway velcro at centre frame retrofit | Applied | Applied | Applied | Applied | Applied | Applied | 100% | BL10.6
CR0061965 | HVBOX main cover damaged during short circuit on TS99 (X63 connector) | NA | NA | Applied | Applied | NA | NA | 100% | BL 10.6
CR0042071 | Lower guide rail removal of machining process | Applied | Applied | Applied | Applied | Applied | Applied | 100% | BL 10.6
CR0042068 | Lower guide rail channel width dimension and toler | Applied | Applied | Applied | Applied | Applied | Applied | 100% | BL 10.6
CR0059823 | UNUSED CAB ROOF ANTENNA INSTALLATION Impacted | Applied | NA | NA | NA | NA | Applied | 100% | BL 10.6
CR0059888 | Partition door is opening while the train is in motion during service. | Applied | NA | NA | NA | NA | Applied | 100% | BL 10.6
CR0039539 | Wheel Flange Lubrication | Applied | Applied | Applied | Applied | Applied | Applied | 100% | BL 10.6
CR0065216 | New emergency escape ladder. | Applied | NA | NA | NA | NA | Applied | 100% | BL 10.5
CR0050154 | Warping Display Glass on Equipped Top End Lining | Applied | Applied | Applied | Applied | Applied | Applied | 100% | BL 10.5
CR0046037 | The Eurobalise cables have too much slack | Applied | NA | NA | NA | NA | Applied | 100% | BL 10.4.1
CR0062201 | Roof TC revert to same installation | Applied | NA | NA | NA | NA | Applied | 100% | BL 10.4.1
CR0057096 | Cab Door lock mechanism design Optimisation / RDTC changes | Applied | NA | NA | NA | NA | Applied | 100% | BL 10.6
| GIB0000006849 | A0 | Change Request Tracker Baseline 10.4_TS223 | [5 empty] | 2024-05-22
| <Reference> | Rev | [6 empty] | 5/5 Pages